## Gaps
Gap ID | Affected system/service (component + file:line) | ZT pillar | Requirement source (document + control/activity ID) | Current state (evidence) | Gap | Risk (H/M/L with rationale) | Proposed corrective action | Responsible Government decision authority (role — e.g., AO, ISSM, Program Office, Enterprise ICAM PMO) | Estimated implementation dependency (what must exist first) | Effort (S/M/L) | Recommended sequence (phase)
G-01 | API JWT verification — api/source/utils/auth.js:74-81 (verifyToken); api/source/utils/jwksCache.js:182-188 (key filtering) | Applications & Workloads | NIST SP 800-53r5 IA-5, SC-23; DoD ZT Capability 3.4 Resource Authorization & Integration; ASD STIG V-222580 (validate session identifiers) | jwt.verify() is called with only an optional {audience} option (auth.js:75-77). No `algorithms` allow-list and no `issuer` option are passed. JWKS keys are filtered to kty RSA/EC/OKP and use=sig (jwksCache.js:182-183), so the library's key-type defaults constrain `alg` (jsonwebtoken ^9.0.2, api/source/package.json:29, derives the accepted set from the key type when no `algorithms` option is passed), but this is implicit rather than an explicit application policy. The expected issuer (STIGMAN_OIDC_PROVIDER, config.js:95) is used only to locate the JWKS URI and is never compared to the token `iss` claim. | No explicit accepted-algorithm list and no issuer (`iss`) validation in the API. A token from any issuer whose key is reachable through the configured JWKS (for example a multi-tenant IdP or a shared JWKS) would be accepted if audience is not configured. | M — Signature verification and key-type filtering are present; the residual exposure is cross-issuer or cross-realm token acceptance when the IdP hosts multiple realms or a shared key set, and the absence of an auditable algorithm policy. | Pass an explicit `algorithms` allow-list (for example RS256, PS256, ES256, EdDSA as approved) and `issuer: config.oauth.authority` to jwt.verify(). Add unit tests for wrong-issuer and wrong-alg rejection. Document the resulting contract in docs/installation-and-setup/authentication.rst. | ISSM (control implementation); Program Office (code change approval) | Confirmed list of approved signing algorithms from the Enterprise ICAM PMO / IdP owner; confirmed issuer string for each target environment. | S | Phase 1
G-02 | API JWT verification — api/source/utils/auth.js:74-81; api/source/utils/config.js:96 (STIGMAN_JWT_AUD_VALUE) | Applications & Workloads | NIST SP 800-53r5 IA-5, SC-23; NIST SP 800-63-4 (assertion audience restriction); DoD ZT Capability 3.4 Resource Authorization & Integration | Audience is validated only when STIGMAN_JWT_AUD_VALUE is set (auth.js:75). The variable has no default (config.js:96). The web client also checks audience only when configured (client/src/js/workers/oidc-worker.js:420). | Audience restriction is opt-in. In a default deployment, any access token signed by the trusted IdP for any other client/resource is accepted by the API. | H — Token-audience confusion allows a token minted for a different relying party on the same IdP to be replayed against this API; the check is a configuration switch that is easy to omit and is not detected at startup. | Make audience validation mandatory: fail startup when STIGMAN_JWT_AUD_VALUE is unset unless an explicit insecure-mode flag is present, or default the audience to the API client identifier. Log a startup warning at minimum. Add a unit test for missing-audience rejection. | ISSM; Program Office | Enterprise IdP client registration that issues tokens with a stable `aud` for this API (IdP audience mapper); deployment configuration change in every environment. | S | Phase 1
G-03 | API JWT verification — api/source/utils/auth.js:74-81 (no clockTolerance / maxAge options) | Applications & Workloads | NIST SP 800-53r5 AC-12, SC-23; ASD STIG V-222580 | jwt.verify() enforces `exp` and `nbf` through library defaults; no clockTolerance or maxAge is configured (auth.js:75-77). Token lifetime is therefore entirely IdP-controlled and no application-side ceiling exists. | The application cannot enforce an organization-defined maximum token lifetime independently of the IdP, and behaviour under clock skew between IdP and API hosts is undocumented. | L — Expiry is enforced; the exposure is limited to IdP misconfiguration (very long-lived tokens) and undocumented skew handling. | Add an optional `maxAge` ceiling and an explicit small `clockTolerance` (for example 30 s) as configuration with documented defaults; document the required IdP token-lifetime settings in authentication.rst. | ISSM | Government-approved session and token lifetime values (see G-16). | S | Phase 2
G-04 | API JWT verification — api/source/utils/auth.js:84-100 (validateToken); no revocation or introspection call | User | DoD ZT Capability 1.8 Continuous Authentication (Single Authentication / Periodic Authentication); NIST SP 800-207 §3 (continual evaluation); NIST SP 800-53r5 AC-12 | Tokens are validated offline against the cached JWKS (auth.js:51-60, 84-100). No token introspection, revocation list, or back-channel logout handling exists. A token remains valid until `exp` regardless of IdP session state. | No mechanism to terminate access before token expiry when a user is disabled, a CAC is revoked, or the IdP session is ended. | M — Exposure window equals the access-token lifetime configured at the IdP; with short-lived tokens the risk is bounded, but the application has no independent control. | Adopt short access-token lifetimes at the IdP as a documented deployment requirement; add optional introspection or back-channel logout support for high-risk deployments; propagate local `status='unavailable'` (UserService.js:338) to reject requests immediately after an administrator disables a user. | AO (risk acceptance of token-lifetime exposure window); Enterprise ICAM PMO (IdP session policy) | Enterprise IdP support for introspection or back-channel logout; approved token lifetime policy. | M | Phase 2
G-05 | Local identity store — api/source/utils/auth.js:110-117 (username precedence); api/source/service/UserService.js:345-351, 500-556; api/source/service/migrations/sql/current/10-stigman-tables.sql (`user_data.username` UNIQUE) | User | DoD Enterprise ICAM Reference Design (persistent unique identifier / master user record); NIST SP 800-53r5 IA-4, IA-8; ASD STIG V-222522, V-222552; DoD ZT Capability 1.5 Identity Federation & User Credentialing | The API selects an identity from the first present claim in [configured username claim, preferred_username, configured service-name claim, azp, client_id, clientId] (auth.js:110-111) and keys the local record on that string (`user_data.username`, UNIQUE). The `sub` claim is not used as the identity key. No EDIPI/DoD ID or certificate identifier column exists. | Identity is a mutable, IdP-scoped display name rather than a persistent unique identifier. Username re-use, renames, or IdP migration can silently merge or split user histories and grants. | H — Username collision across IdP migrations or between a person and an NPE client would transfer collection grants and audit history to the wrong subject. | Add an immutable identity key (for example `sub` plus issuer, or an enterprise persistent identifier such as EDIPI/DoD ID when furnished in the assertion) to `user_data`; migrate existing records with a Government-approved mapping; keep `username` as a display attribute only. | Enterprise ICAM PMO (attribute standard); Program Office (schema change); AO (migration risk) | Enterprise IdP assertion profile that includes a persistent identifier; approved attribute-mapping specification (DAF ICAM direction — Needs Government input). | L | Phase 2
G-06 | First-login provisioning — api/source/utils/auth.js:117-140; api/source/service/UserService.js:345-351 (INSERT INTO user_data) | User | NIST SP 800-53r5 AC-2, AC-2(1); ASD STIG V-222413, V-222467; DoD ZT Capability 1.5 Organizational Identity Life-Cycle Management | Any subject that presents a valid token with the required scope is inserted into `user_data` on first request (auth.js:117, UserService.js:351). There is no approval step, no allow-list, and no automatic disable on inactivity (`lastAccess` is recorded but not acted on). | Account creation is implicit and unbounded by anything other than IdP token issuance; the application cannot enforce organization-defined account authorization, and no account-creation audit record distinct from the request log is written. | M — Acceptable when the IdP client is tightly scoped to authorized users; otherwise every IdP user becomes an application user. Inactivity disable relies entirely on the IdP. | Emit an explicit `account-created` audit event with subject/source/outcome; add an optional configuration to require pre-provisioning or a group/role claim for first login; document that account-lifecycle (disable after inactivity, removal) is enforced by the enterprise IdP and must be verified in the ATO. | ISSM; Enterprise ICAM PMO | Enterprise group/role attribute available in the assertion (G-05); logging changes (G-11). | M | Phase 2
G-07 | Non-person entity handling — api/source/utils/auth.js:110-111 (azp/client_id/clientId fallback); api/source/utils/config.js:104 (STIGMAN_JWT_SERVICENAME_CLAIM has no default); docs/installation-and-setup/authentication.rst:28,110 | User | DoDI 8520.03 §3.4 (NPE authentication) and §3.4.e (NPE authentication as a provisioned user); DoD Enterprise ICAM Reference Design (NPE identity); NIST SP 800-53r5 IA-9 | Service accounts are mapped to the same `user_data` table using the client identifier as the username (auth.js:110-111). Documentation states the service-name claim defaults to `clientId` (authentication.rst:28) while the code has no default (config.js:104); the hard-coded fallback list supplies the same behaviour. | NPEs and persons share one identity namespace and one privilege model; there is no NPE-specific credential policy (certificate-based client authentication, rotation) enforced or documented, and no marker distinguishing NPE records. | M — An NPE client name equal to a person's username would collide (see G-05); NPE credentials are governed only by the IdP. | Add an `entityType` attribute to local identities derived from the token (client-credentials grant vs. person); require NPE clients to authenticate to the IdP with a DoD-approved certificate credential; align documentation with code for the service-name claim. | Enterprise ICAM PMO (NPE credential policy); ISSM | G-05 persistent identifier; IdP configured for certificate-bound client authentication. | M | Phase 2
G-08 | Privilege mapping — api/source/utils/auth.js:142-149; api/source/utils/config.js:106-108 (STIGMAN_JWT_PRIVILEGES_CLAIM default realm_access.roles) | User | NIST SP 800-53r5 AC-6, AC-6(1), AC-6(5); DoD ZT Capability 1.2 Conditional User Access (App Based Permissions per Enterprise); ASD STIG V-222429 | Application privileges are exactly two string values, `admin` and `create_collection`, read from a configurable claim path defaulting to Keycloak's `realm_access.roles` (auth.js:142-145). Any token from the trusted IdP that carries these strings receives the privilege. | Privilege is a coarse two-value role list with a Keycloak-specific default path. There is no mapping layer from enterprise groups/attributes to application privileges, and no support for conditional or attribute-based grant of `admin`. | M — Functionally sound but IdP-specific; migration to an enterprise IdP requires either a custom claim mapper at the IdP or configuration changes in every environment. | Externalise privilege mapping (enterprise group or attribute → application privilege) into configuration or an admin-managed table; document required IdP mappers for the enterprise IdP; keep `realm_access.roles` as a compatible default. | Enterprise ICAM PMO (group naming and attribute release); Program Office | Enterprise IdP group/attribute claim specification (Needs Government input). | M | Phase 2
G-09 | Elevated administration and self-grant — api/source/controllers/Collection.js:389-405 (getCollectionInfoAndCheckPermission); api/source/controllers/Collection.js:298; docs/installation-and-setup/data-and-permissions.rst:177-191 | User | NIST SP 800-53r5 AC-5, AC-6(1), AC-6(9), AC-6(10); DoD ZT Capability 1.4 Privileged Access Management; ASD STIG V-222431, V-222450, V-222454 | Users with the `admin` privilege pass `?elevate=true` to bypass collection-grant checks for management operations (Collection.js:389-405). Documentation confirms an elevated admin may grant themselves any role in any collection and states that the accepted control is that elevated request/response bodies are written to the application log (data-and-permissions.rst:189-191). Elevation is per-request and does not require re-authentication. | No separation of duties between the role that manages grants and the role that consumes collection content; no re-authentication or step-up for privileged operations; no break-glass procedure or dual-authorisation option. | H — A single `admin` role can obtain full read/write access to any collection by self-grant. The compensating control is after-the-fact log review, which depends on deployment log retention and review (G-12). | Add a configurable policy that (a) denies self-grant by default and requires a second admin, (b) requires step-up re-authentication (fresh `auth_time` or `acr` claim) for `elevate=true`, and (c) emits a distinct `privilege-change` audit event. Document a break-glass procedure for the deployment. | AO (accept or reject the current compensating control); ISSM (break-glass procedure) | IdP support for step-up authentication claims (`acr`/`auth_time`); structured audit events (G-11). | M | Phase 1
G-10 | Scope matching — api/source/utils/auth.js:161-185 (validateOauthSecurity); api/source/specification/stig-manager.yaml:10892-10900 (securitySchemes) | Applications & Workloads | NIST SP 800-53r5 AC-3, AC-6; DoD ZT Capability 1.7 Least Privileged Access (Deny User by Default Policy); ASD STIG V-222425 | Every operation in the OpenAPI specification declares required `stig-manager:*` scopes and the handler is enforced by express-openapi-validator (middlewares.js:111). Granted scopes match if equal or if the granted scope is a prefix of the required scope by colon-separated tokens (auth.js:170-178), so `stig-manager:collection` satisfies `stig-manager:collection:read`. | Scope enforcement is well-structured, but the prefix rule means a broad parent scope grants every child operation; there is no documentation of the minimum scope set per role and no test asserting that unexpected scope strings are rejected. | L — Behaviour is deliberate and consistent; the residual risk is over-broad scope issuance at the IdP. | Publish a least-privilege scope matrix (role → minimum scopes) in authentication.rst; add unit tests for prefix matching and rejection of unrelated scopes; recommend IdP client scope restrictions per client. | ISSM | None (documentation and tests). | S | Phase 1
G-11 | Security event logging — api/source/utils/logger.js:79-93 (serializeRequest), 155-183 (transaction/response records); api/source/bootstrap/errorHandlers.js:13-17; api/source/utils/logSocket.js:190-191 | Visibility & Analytics | NIST SP 800-53r5 AU-2, AU-3, AU-12; ASD STIG V-222450, V-222454, V-222462, V-222463, V-222477; DoD ZT Capability 7.1 Log All Traffic (Log Parsing) | Every request produces a structured JSON record with requestId, date, source IP, method, URL, headers and (in combined mode) response status and operation statistics (logger.js:79-93, 160-171). Application security errors (SmError, including PrivilegeError, OutOfScopeError, NoTokenError) are returned to the client but are not written as distinct error events; only non-application errors are logged at errorHandlers.js:13-17. The HTTP status appears in the transaction record. There is no dedicated event type for logon, logoff, privilege change, grant change, account creation or data export. | Security-relevant events must be reconstructed from generic transaction records by URL pattern and status code. No first-class audit events exist with subject, object, action, outcome and source fields, which complicates SIEM parsing and AU-6 review. | M — Data needed for reconstruction is mostly present (subject via userObject, source IP, URL, status) but not normalised; failed authorization is logged only as a transaction with a 403 status. | Add an `audit` event type emitted by the API for: authentication accepted/rejected, authorization denied (scope, privilege, grant), account created/modified/disabled, grant created/modified/deleted, elevated request, data export, and admin operations. Each event carries subject (userId, username, persistent id), object (collectionId/assetId/userId), action, outcome, source IP and requestId. Publish the JSON schema alongside the existing logging schema. | ISSM (auditable event list per AU-2); Program Office | Government-approved auditable-event list; SIEM parser update. | M | Phase 1
G-12 | Log retention, protection and review — docs/installation-and-setup/logging.rst:8 (STDOUT JSON); docs/installation-and-setup/data-and-permissions.rst:189-191 (log review as compensating control) | Visibility & Analytics | NIST SP 800-53r5 AU-6, AU-9, AU-11; ASD STIG V-222481, V-222482; DoD ZT Capability 7.2 Security Information and Event Management (SIEM) | The application writes JSON to STDOUT only (logging.rst:8). Collection, forwarding, retention, integrity protection and review are deployment responsibilities and are not specified. | The security model for elevated administration depends on log review, but no requirement for SIEM forwarding, retention period, or review cadence is stated for the deployment. | M — Without enforced forwarding and review, the compensating control for G-09 does not exist in practice. | Add a deployment security baseline that requires container log forwarding to the enterprise SIEM, retention per Government policy, and a documented review procedure for `elevate=true` transactions and audit events; add SIEM parsing rules for the new audit event type. | ISSM; AO (retention and review cadence) | Enterprise SIEM onboarding; G-11 audit events. | S | Phase 1
G-13 | Sensitive data in logs — api/source/utils/logger.js:62-76 (sanitizeHeaders decodes bearer payload), 81-83 (accessToken added in combined mode), 91 (request body logged for elevate or log level 4) | Visibility & Analytics | ASD STIG V-222444 (must not write sensitive data into logs); NIST SP 800-53r5 AU-3(3), SC-28 | The bearer token itself is replaced by `authorization: true`, but the decoded token payload (all claims) is attached to the request record as `headers.accessToken` in every mode (logger.js:68-69, 81-83). Full request bodies are logged for elevated requests and at log level 4 (logger.js:91), and full response bodies in combined mode (logger.js:168). | Logs contain every identity claim released by the IdP (email, names, roles, any custom attributes) and, for elevated requests, complete request/response payloads. If the enterprise IdP releases additional PII attributes, they will be written to logs unfiltered. | M — Signature is stripped so tokens cannot be replayed from logs, but PII exposure and log volume grow with the enterprise attribute set. | Replace the full decoded payload with a fixed subject block (sub/persistent id, username, azp, scope, exp, jti); keep body logging for elevated requests but redact configured sensitive fields; document the log data classification. | ISSM; Privacy Officer (PII in logs) | Enterprise attribute release list (Needs Government input). | S | Phase 2
G-14 | Web client token handling — client/src/js/workers/oidc-worker.js:55 (logs authorization code and PKCE verifier), :542 (logs full token response) | User | ASD STIG V-222444, V-222577 (must not expose session identifiers); NIST SP 800-53r5 IA-5(7), SC-28 | The OIDC worker writes the authorization code and PKCE code_verifier (oidc-worker.js:55) and the complete token endpoint response including access and refresh tokens (oidc-worker.js:542) to the browser console. | Credentials are exposed in browser developer tooling and in any console-capture mechanism (browser telemetry, screen recording, support tooling). | M — Exploitation requires access to the user's browser session or console logs; refresh tokens in the console extend the exposure beyond the access-token lifetime. | Remove token, code and verifier values from console output; log only event names and timestamps. Add a unit test or lint rule that fails on logging of `tokensResponse`, `code`, or `codeVerifier`. | Program Office | None. | S | Phase 1
G-15 | Web client authorization flow — client/src/js/workers/oidc-worker.js:205 (strict PKCE check), :267 (S256), :420-421 (audience and claim validation), :115-118 (logout via end_session_endpoint); api/source/utils/config.js:45 (STIGMAN_CLIENT_STRICT_PKCE) | User | NIST SP 800-63-4 (federation assertion handling); ASD STIG V-222391 (logoff capability), V-222578; NIST SP 800-53r5 AC-12(1) | Authorization Code with PKCE S256 is enforced when strictPkce is true (default) and the worker refuses providers that do not advertise S256 (oidc-worker.js:205, 267). Tokens are held in worker memory, not in storage. Logout redirects to the provider end_session_endpoint (oidc-worker.js:115-118). PKCE can be disabled by setting STIGMAN_CLIENT_STRICT_PKCE=false (config.js:45). | The flow is current-practice; the only gap is that strict PKCE is a runtime switch rather than fixed, and logout does not revoke the refresh token at the IdP (relies on end-session). | L — Defaults are secure; risk arises only if a deployment disables strict PKCE. | Remove or deprecate the option to disable strict PKCE in production builds; call the IdP revocation endpoint (if advertised) for the refresh token on logout; document the required IdP client settings (public client, PKCE required, no implicit flow). | ISSM | None. | S | Phase 2
G-16 | Session lifetime and idle timeout — client/src/js/workers/oidc-worker.js:335-410 (refresh timers), :457-490 (validateClaims, idle timeout by privilege), :575-585; api/source/utils/config.js:26-36 (STIGMAN_CLIENT_USER_TIMEOUT, STIGMAN_CLIENT_ADMIN_TIMEOUT default 0) | User | NIST SP 800-53r5 AC-11, AC-12; ASD STIG V-222389 (15-minute non-privileged idle), V-222390 (10-minute admin idle); DoD ZT Capability 1.8 Continuous Authentication | The client implements separate idle timeouts for admin and non-admin users, but both default to 0 (disabled) unless STIGMAN_CLIENT_USER_TIMEOUT / STIGMAN_CLIENT_ADMIN_TIMEOUT are set (config.js:26-36, oidc-worker.js:471-476). Access-token refresh continues automatically while the refresh token is valid (oidc-worker.js:335-410). Idle timeout is enforced client-side only; the API has no session concept beyond token expiry. | Idle timeouts are disabled by default and are enforced only in the browser; the API cannot enforce an inactivity limit independently of the IdP's refresh-token policy. | M — Default configuration does not meet the STIG idle-timeout values; a deployment must remember to set both variables and configure matching IdP session limits. | Set secure defaults (15 min user, 10 min admin) and require explicit opt-out; document the paired IdP settings (SSO idle, refresh-token lifetime, access-token lifetime) that make the server-side limit effective; consider adding `auth_time`/`iat` age checks at the API for privileged operations. | ISSM; AO (approve timeout values) | Government-approved session lifetime values; IdP configuration control. | S | Phase 1
G-17 | CAC/PIV and MFA path — docs/installation-and-setup/installation-and-setup.rst:57-62 (reverse proxy required for mTLS/CAC/PKI); api/source/bootstrap/server.js:45-48 (native TLS without client certificate options) | User | DoDI 8520.03 §3.2.b-c, §3.3 (person entity authentication; DoD-approved PKI / AAL2-AAL3 assertions); NIST SP 800-53r5 IA-2(1), IA-2(2), IA-2(12); ASD STIG V-222523, V-222526, V-222550, V-222552, V-222559; DoD ZT Capability 1.3 MFA (Organizational MFA/IDP) | The application performs no direct authentication; it relies entirely on OIDC assertions. CAC/PIV authentication, certificate path validation and revocation checking occur at the IdP or a reverse proxy in front of it (installation-and-setup.rst:57-62). The API does not inspect `acr`, `amr` or `auth_time` claims, so it cannot distinguish a CAC-authenticated session from a password session issued by the same IdP. | The application has no assurance-level awareness. It cannot require or verify that the assertion was produced by a DoD-approved PKI credential, and the CAC → IdP → application flow is undocumented for the enterprise IdP. | H — Meeting DoDI 8520.03 for moderate/high-risk resources depends entirely on IdP configuration that the application neither checks nor documents; a mis-configured IdP realm with password login enabled would be indistinguishable to the API. | Document the CAC/PIV path end-to-end (browser → IdP X.509 authenticator → OIDC assertion with `amr`/`acr` → API). Add optional API enforcement of a required `acr`/`amr` value (configurable) and expose it in the audit event. Confirm the IdP is an approved DoD IdP or reverse-proxy IdP per DoDI 8520.03 §3.6. | AO (resource risk level per DoDI 8520.03 §3.3); Enterprise ICAM PMO (approved IdP and assertion profile) | Enterprise IdP assertion profile including authentication-context claims (Needs Government input); DAF ICAM direction on approved IdPs. | M | Phase 2
G-18 | Single IdP client / realm configuration — api/source/utils/config.js:37, 89, 95 (default authority http://localhost:8080/realms/stigman); api/source/specification/stig-manager.yaml:10895 (openIdConnectUrl literal); client/src/js/Env.js.example | Applications & Workloads | DoD Enterprise ICAM Reference Design (enterprise IdP federation); NIST SP 800-53r5 IA-8; DoD ZT Capability 1.9 Integrated ICAM Platform (Enterprise PKI/IDP Pt1); ASD STIG V-222560 | One OIDC authority is configured for the API, one for the web client and one for the OpenAPI UI (config.js:37, 89, 95). Defaults point at a local Keycloak realm named `stigman`. The OpenAPI document embeds a literal Keycloak discovery URL (stig-manager.yaml:10895). Only one issuer/JWKS is supported at a time. | Single-issuer design with Keycloak-specific defaults. Federation scenarios (enterprise IdP plus a mission-partner IdP, or migration with an overlap period) are not supported without a broker in front of the application. | M — Enterprise integration is feasible by pointing the authority at the enterprise IdP or a broker, but multi-issuer operation and issuer pinning (G-01) are absent, and defaults are non-production values. | Remove non-production defaults from production images (fail fast when unset); support a small list of trusted issuers with per-issuer JWKS and audience; generate the OpenAPI `openIdConnectUrl` from configuration at startup. | Enterprise ICAM PMO (federation pattern: direct vs. broker); Program Office | Decision on federation topology; G-01 issuer validation. | M | Phase 3
G-19 | Attribute-based access control — api/source/controllers/Collection.js:389-405 (grant/role check); api/source/utils/roles.js:1-6 (numeric roles Restricted=1 … Owner=4); api/source/service/migrations/sql/current/10-stigman-tables.sql (collection_grant, user_group) | Applications & Workloads | DoD ZT Capability 3.4 Resource Authorization & Integration (Enrich Attributes for Resource Authorization Pt1); NIST SP 800-207 §3.1 (policy engine / policy administrator); NIST SP 800-53r5 AC-3(13) attribute-based access control | Authorization is RBAC: collection grants assign one of four ordered roles to a user or user group, with optional ACLs within a collection (Collection.js:389-405, roles.js). Decisions are made in controllers and services using locally stored grants; there is no policy decision point and no use of enterprise attributes (organisation, clearance, duty position) at decision time. | No externalised policy decision point and no attribute inputs beyond the local grant table; ABAC or conditional access (device posture, location, risk score) cannot be expressed without code change. | M — RBAC is adequate for current use; Target-level ZT activities for resource authorization enrichment are not met. | Introduce an authorization abstraction (policy enforcement point) around getCollectionInfoAndCheckPermission and the user/grant controllers that can consult an external policy decision point (for example OPA or the enterprise PDP) with token attributes and request context; keep local RBAC as the fallback policy. | Enterprise ICAM PMO (enterprise PDP/attribute service availability); Program Office; AO | Enterprise attribute source and PDP available to the application enclave; G-05 and G-08 attribute mapping. | L | Phase 3
G-20 | API transport security — api/source/bootstrap/server.js:10-48 (HTTPS only when STIGMAN_API_TLS_KEY_FILE and STIGMAN_API_TLS_CERT_FILE are set); docs/installation-and-setup/installation-and-setup.rst:106 | Network & Environment | NIST SP 800-53r5 SC-8, SC-8(1), SC-23; ASD STIG V-222396, V-222397, V-222584 | Native HTTPS is optional; the server falls back to plain HTTP when TLS files are not configured (server.js:45-48). Documentation requires HTTPS for non-localhost use and recommends a reverse proxy (installation-and-setup.rst:106). No minimum TLS version or cipher policy is set in code (Node defaults apply). | Transport protection depends on deployment; the application does not enforce TLS 1.2+ or DoD-approved certificate authorities itself and does not refuse to start without TLS. | M — Standard for containerised services behind a terminating proxy, but a direct-exposure deployment could run unencrypted. | Add a production mode that refuses plain HTTP unless an explicit proxy-terminated flag is set; pin minVersion TLSv1.2 (or 1.3) and FIPS-approved cipher suites when native TLS is used; document the DoD PKI trust store requirement for the proxy or native listener. | ISSM; AO (TLS termination point) | Deployment architecture decision (native TLS vs. proxy/ingress). | S | Phase 1
G-21 | Database connection identity — api/source/service/utils.js:187-197 (TLS only when CA/cert/key configured); api/source/utils/config.js:73-79 (STIGMAN_DB_PASSWORD); docs/installation-and-setup/db.rst:125-136 (client certificate authentication) | Network & Environment | DoD ZT Capability 5.x Network & Environment (data-flow protection) and 2.x Device (workload identity as applied to service-to-service); DoDI 8520.03 §3.4.a (NPE mutually authenticated transactions); NIST SP 800-53r5 SC-8, IA-9; ASD STIG V-222534 | MySQL TLS is enabled only when at least one of CA, certificate or key file is configured (utils.js:187-197). The API supports X.509 client-certificate authentication to MySQL as an alternative to a password (db.rst:125-136). Default configuration is a static password in an environment variable with no TLS. | Mutual TLS between API and database is available but optional; the default is password-based, unencrypted database access. | M — Within a private network segment the exposure is limited; the default does not meet the mutual-authentication expectation for service-to-service traffic. | Make database TLS with server-certificate verification the default, and adopt X.509 client-certificate authentication for the API service identity; fail startup when neither TLS nor an explicit insecure flag is present. | ISSM; Program Office | Enclave PKI able to issue service certificates; database configured to require TLS. | M | Phase 2
G-22 | Secrets and workload identity in deployment assets — api/source/utils/config.js:74 (STIGMAN_DB_PASSWORD), :63-66 and :76-79 (file paths for TLS material); Dockerfile; docs/installation-and-setup/ | Device | DoD ZT Capability 2.x Device / 3.x Applications & Workloads (workload identity, secrets handling); NIST SP 800-53r5 IA-5(7), SC-12, SC-28; ASD STIG V-222642 (no embedded authentication data) | No credentials are embedded in source; all secrets arrive as environment variables or mounted files (config.js:63-79). No secrets-manager or workload-identity integration exists; rotation is a deployment concern. Container images run the API directly from the Dockerfile with no secret retrieval step. | Secrets lifecycle (issuance, rotation, revocation) and workload identity are entirely outside the application; no guidance ties them to an enterprise secrets manager or service mesh identity. | L — Environment-variable injection is the common container pattern; risk depends on the orchestrator's secret handling. | Document a reference deployment that sources STIGMAN_DB_PASSWORD (or preferably the client certificate) and TLS keys from the platform secrets manager with rotation; adopt certificate-based database identity (G-21) to eliminate the password entirely. | ISSM; Platform/Hosting owner | Platform secrets manager and PKI issuance for workloads. | S | Phase 2
G-23 | Data export events — api/source/controllers/Collection.js:105-108 (exportCollections), :1030-1037 (exportToCollection operation in stig-manager.yaml); checklist download operations (stig-manager.yaml:227, 256, 977) | Data | NIST SP 800-53r5 AU-2, AC-4, AC-21; ASD STIG V-222471 (log user actions involving access to data); DoD ZT Capability 4.x Data (data monitoring) | Collection export, checklist download and cross-collection copy are ordinary authenticated operations recorded only as request/transaction log entries (logger.js:155-183). There is no data classification or labelling of exported artifacts and no export-specific audit event. | Bulk data egress is indistinguishable from routine reads in the logs; no export approval or marking control exists. | L — Data is STIG compliance data whose sensitivity is determined by the Government; the gap is visibility rather than enforcement. | Emit `data-export` audit events (subject, collection, format, record count); add optional export marking/banner text from configuration; include export events in SIEM alerting rules. | Data Owner / ISSM (classification of compliance data) | G-11 audit events; Government data-classification decision. | S | Phase 2
G-24 | Insecure-token allowance — api/source/utils/auth.js:44-49 (checkInsecureKid); api/source/utils/config.js:4, 97-99 (STIGMAN_DEV_ALLOW_INSECURE_TOKENS, insecureKids list) | Applications & Workloads | NIST SP 800-53r5 CM-7, IA-5; ASD STIG V-222662 (default credentials), V-222642 | Tokens signed with a known test key ID are rejected unless STIGMAN_DEV_ALLOW_INSECURE_TOKENS=true (auth.js:45-46). The known insecure kid is hard-coded (config.js:4). This is a deliberate guard against shipping the test IdP key into production. | The guard is positive, but the bypass is a plain environment flag with no startup warning and no audit event when enabled. | L — Requires deliberate misconfiguration; a startup warning would make it visible. | Log a persistent WARN at startup and in every audit event when insecure tokens are allowed; exclude the flag from production container defaults; add a unit test that the insecure kid is rejected by default. | ISSM | None. | S | Phase 1
G-25 | Automation of identity governance — api/source/controllers/User.js:25-31 (elevate required for user management); api/source/service/UserService.js:338 (status unavailable); no scheduled job or SCIM/provisioning API | Automation & Orchestration | DoD ZT Capability 6.x Automation & Orchestration (policy and identity automation); NIST SP 800-53r5 AC-2(1), AC-2(3), AC-2(4); ASD STIG V-222411, V-222415 | User status changes and grant management are manual API operations by an elevated admin (User.js:25-31). No SCIM endpoint, no inbound deprovisioning hook, and no scheduled inactivity review exist. `lastAccess` is recorded (UserService.js:505) but nothing acts on it. | Joiner/mover/leaver events at the enterprise IdP are not propagated to local grants; orphaned grants persist until an administrator removes them. | M — Disabled enterprise users cannot obtain tokens, so access is blocked, but their grants and history remain and are re-activated if the username is re-used (G-05). | Add a configurable inactivity job that sets `status='unavailable'` after N days without access and emits an audit event; add an administrative bulk-reconciliation endpoint or SCIM-style deprovisioning hook the enterprise IdP or an orchestrator can call. | Enterprise ICAM PMO (provisioning integration pattern); ISSM (inactivity threshold) | G-05 persistent identifier; enterprise provisioning or event feed availability. | M | Phase 3
G-26 | DAF-specific ICAM alignment — whole application; no repository evidence (policy source not public) | User | Needs Government input — DAF ICAM implementation direction and DAF Enterprise Zero Trust Roadmap (documents located by title only; not opened from the assessment environment) | Publicly available material describes DAF enterprise identity services at a high level only (an authoritative identity data service and a published DAF Zero Trust strategy and roadmap). No public document specifies the DAF-required IdP, assertion profile, attribute set, or identifier for applications of this type. | The assessment cannot confirm alignment with DAF-specific ICAM requirements. Rows G-05, G-08, G-17 and G-18 are structured so the Government-furnished direction replaces the assumptions recorded here. | M — Uncertainty rather than a known defect; the integration design cannot be finalised until direction is furnished. | Government to furnish the DAF ICAM integration specification (approved IdP endpoints, client registration process, assertion claims including persistent identifier and authentication context, attribute release, logging destination). Re-baseline G-05, G-08, G-17, G-18 against it. | Enterprise ICAM PMO; Program Office | Receipt of Government-furnished DAF ICAM direction. | S | Phase 0

## Control-Crosswalk
NIST SP 800-53r5 control | Title | Status | Evidence | Related gaps
IA-2 | Identification and Authentication (Organizational Users) | Partially | All API access requires a bearer token validated against the IdP JWKS (auth.js:84-100). Identification is by username claim, not persistent identifier (auth.js:110-111). | G-05, G-17
IA-2(1) | MFA to Privileged Accounts | Needs Government input | Application does not authenticate directly; MFA is an IdP property. No `acr`/`amr` check in API. | G-17
IA-2(2) | MFA to Non-Privileged Accounts | Needs Government input | As IA-2(1). | G-17
IA-2(12) | Acceptance of PIV Credentials | Needs Government input | PIV/CAC acceptance occurs at the IdP or reverse proxy (installation-and-setup.rst:57-62); application has no visibility. | G-17
IA-4 | Identifier Management | Not satisfied | Local identifier is the mutable username string; no persistent unique identifier stored (10-stigman-tables.sql user_data). | G-05
IA-5 | Authenticator Management | Partially | Signature verification with JWKS rotation (jwksCache.js); no explicit alg/issuer policy (auth.js:74-81); audience optional (config.js:96). | G-01, G-02, G-24
IA-8 | Identification and Authentication (Non-Organizational Users) | Partially | Any IdP-issued identity is accepted and auto-provisioned; distinction between organizational and non-organizational users depends on IdP. | G-06, G-18
IA-9 | Service Identification and Authentication | Partially | NPE clients map to users via azp/client_id (auth.js:110-111); DB client-certificate authentication available but optional (db.rst:125-136). | G-07, G-21
AC-2 | Account Management | Partially | Accounts auto-created at first login (UserService.js:351); status field supports disable (UserService.js:338); no inactivity automation. | G-06, G-25
AC-3 | Access Enforcement | Satisfied | OpenAPI scope enforcement on every operation (middlewares.js:111, auth.js:161-185) and collection-grant checks (Collection.js:389-405). | G-10
AC-5 | Separation of Duties | Not satisfied | Single `admin` privilege can self-grant any collection role (data-and-permissions.rst:189-191). | G-09
AC-6 | Least Privilege | Partially | Four-level collection roles and scoped API operations; elevation is per-request and broad. | G-08, G-09, G-10
AC-6(1) | Authorize Access to Security Functions | Partially | Security functions require `admin` + `elevate=true` (User.js:25-26); no step-up authentication. | G-09
AC-6(9) | Log Use of Privileged Functions | Partially | Elevated requests log full request/response bodies (logger.js:91, 160-171); no distinct audit event type. | G-09, G-11
AC-6(10) | Prohibit Non-Privileged Users from Executing Privileged Functions | Satisfied | InvalidElevationError when non-admin requests elevate (auth.js:147-148); PrivilegeError on user management without elevate (User.js:26).
AC-7 | Unsuccessful Logon Attempts | Needs Government input | Logon attempts occur at the IdP; application never sees credentials. | G-17
AC-11 | Device Lock | Partially | Client idle timeout exists but defaults to disabled (config.js:26-36). | G-16
AC-12 | Session Termination | Partially | Logout via IdP end_session_endpoint (oidc-worker.js:115-118); no server-side revocation; token valid until exp. | G-04, G-15, G-16
AC-17 | Remote Access | Partially | HTTPS optional in code (server.js:45-48); documentation requires HTTPS for non-localhost. | G-20
AU-2 | Event Logging | Partially | All requests/responses logged as JSON (logger.js:100-183); no first-class security events for logon, privilege or grant change, export. | G-11, G-23
AU-3 | Content of Audit Records | Partially | Records include time, source IP, method/URL, requestId, status, user id via operation stats; subject/object/outcome not normalised. | G-11, G-13
AU-6 | Audit Record Review, Analysis, and Reporting | Needs Government input | Review is a deployment responsibility; documentation relies on it as the compensating control for self-grant. | G-12
AU-12 | Audit Record Generation | Partially | Generation is centralised in logger.js; event set is generic rather than the AU-2 defined list. | G-11
SC-8 | Transmission Confidentiality and Integrity | Partially | TLS available for API (server.js) and DB (utils.js:187-197) but both optional. | G-20, G-21
SC-23 | Session Authenticity | Partially | Signed JWT with kid lookup and PKCE; missing issuer/audience-by-default checks. | G-01, G-02, G-03

## ZT-Pillar-Summary
ZT pillar | As-is | Target | Gap count | High | Medium | Low | Gap IDs
User | OIDC bearer authentication delegated to a single IdP; username-keyed local identities; two-value privilege model; per-request elevation with self-grant; client-side idle timeout disabled by default. | Enterprise IdP federation with persistent identifier and authentication-context claims; PAM-style step-up for elevation; enforced idle/session limits; NPE identities distinguished. | 11 | 3 | 7 | 1 | G-04, G-05, G-06, G-07, G-08, G-09, G-14, G-15, G-16, G-17, G-26
Device | No device identity or posture input; secrets and TLS material injected by the platform. | Workload identity from enclave PKI/secrets manager; device posture available to the PDP as an authorization attribute (via enterprise IdP conditional access). | 1 | 0 | 0 | 1 | G-22
Applications & Workloads | Scope-per-operation enforcement via OpenAPI; RBAC grants; signature verification with optional audience; single-issuer configuration with non-production defaults. | Explicit alg/issuer/audience policy; multi-issuer trust list; PEP abstraction able to call an enterprise PDP with enriched attributes. | 7 | 1 | 3 | 3 | G-01, G-02, G-03, G-10, G-18, G-19, G-24
Data | Exports and downloads logged as generic transactions; no marking. | Export audit events and configurable marking; SIEM rules for bulk egress. | 1 | 0 | 0 | 1 | G-23
Network & Environment | TLS optional for API and DB; mTLS to DB supported but not default. | TLS enforced for API listener or documented proxy termination; mTLS/certificate identity to DB by default. | 2 | 0 | 2 | 0 | G-20, G-21
Automation & Orchestration | Manual user status and grant management; no provisioning integration. | Inactivity automation, deprovisioning hook, reconciliation with enterprise identity events. | 1 | 0 | 1 | 0 | G-25
Visibility & Analytics | Structured JSON request/transaction logs to STDOUT; decoded token claims in every record; deployment-owned forwarding. | Normalised audit events (subject/object/action/outcome/source) with PII minimisation; mandatory SIEM forwarding and review procedures. | 3 | 0 | 3 | 0 | G-11, G-12, G-13

## Roadmap
Phase | Name | Activities | Dependencies | Government decision needed | Gaps addressed
Phase 0 | Mobilise and baseline | Receive Government-furnished DAF ICAM direction; confirm resource risk level per DoDI 8520.03 §3.3; confirm approved IdP; agree auditable-event list; establish test environment with the approved IdP. | None (entry point). | Enterprise ICAM PMO: furnish IdP, assertion profile and attribute release. AO: resource risk level. ISSM: auditable events. | G-26
Phase 1 | Harden the existing contract | Mandatory audience; explicit algorithms and issuer; secure timeout defaults; audit event type; SIEM forwarding baseline; remove console token logging; TLS production mode; insecure-token startup warning; scope matrix and tests; self-grant policy and step-up design. | Phase 0 decisions on algorithms, issuer strings, audience, timeout values. | ISSM/Program Office: approve code changes. AO: accept or reject self-grant compensating control. | G-01, G-02, G-09, G-10, G-11, G-12, G-14, G-16, G-20, G-24
Phase 2 | Enterprise identity integration | Persistent identifier in user_data with migration; NPE entity type and certificate-bound clients; privilege mapping from enterprise groups; acr/amr enforcement option; token lifetime ceilings; DB mTLS default; secrets-manager reference deployment; log PII minimisation; export events. | Phase 1 complete; enterprise IdP test realm issuing the agreed claims; enclave PKI for service certificates. | Enterprise ICAM PMO: identifier and group standard. AO: migration risk. Privacy Officer: log attribute set. | G-03, G-04, G-05, G-06, G-07, G-08, G-13, G-15, G-17, G-21, G-22, G-23
Phase 3 | Policy externalisation and federation | PEP abstraction with optional enterprise PDP; multi-issuer trust list; inactivity automation and deprovisioning hook; remove Keycloak-specific defaults from production images. | Phase 2 attribute mapping; enterprise PDP/attribute service reachable from the enclave. | Enterprise ICAM PMO: PDP pattern and federation topology. Program Office: scope. | G-18, G-19, G-25
Phase 4 | Validate and authorise | Execute the ICAM test plan in the Government-approved environment; SIEM rule validation; ATO evidence package; residual-risk acceptance. | Phases 1-3 delivered to the test environment. | AO: authorisation decision and residual-risk acceptance. ISSM: test witness and evidence.

## Method
Item | Description
Assessment type | Source-code and documentation review of the repository at the baseline commit; no runtime testing against a Government environment.
Baseline commit | c0662050
Scope | Authentication (OIDC/JWT), authorization (scopes, grants, elevation), auditability, session and credential handling, privileged access, legacy patterns, workload identity and transport security.
Evidence convention | path:line references are to files in this repository at the baseline commit. Line numbers drift with edits; re-verify before citing externally.
Risk scale | H = exploitable weakness or non-compliance likely to block authorization; M = weakness with a compensating control or bounded exposure; L = hardening or documentation item.
Effort scale | S = under one engineering week; M = one to four weeks; L = more than four weeks or requires schema/data migration.
Crosswalk statuses | Satisfied / Partially / Not satisfied / Needs Government input
DAF ICAM direction | Not publicly available. Rows citing it are marked 'Needs Government input' and are to be re-baselined when direction is furnished.
Source verification | Each URL in the Sources sheet was opened from the assessment environment and matched to the cited title; sources that could not be opened are listed without a URL.
Reproducibility | python3 docs/security/icam-zero-trust/scripts/icam_gap_register.py regenerates the workbook from this data file; --check verifies the Markdown assessment stays synchronised.
Gap count (derived) | 26 total: H=4, M=16, L=6

## Sources
Source ID | Title | URL (verified) or blank | Verification note
DoD-ZTS | DoD Zero Trust Strategy, Version 1.0 (October 21, 2022; cleared for open publication November 7, 2022) | https://dodcio.defense.gov/Portals/0/Documents/Library/DoD-ZTStrategy.pdf | Opened in browser; 37-page PDF titled 'DoD Zero Trust Strategy', dated October 21, 2022.
DoD-ZTER | DoD Zero Trust Capability Execution Roadmap (COA 1), 15 November 2022 | https://dodcio.defense.gov/Portals/0/Documents/Library/DoD-ZTExecutionRoadmap.pdf | Opened in browser; 58-page PDF. Capability and activity names cited from the roadmap slides.
DoD-ICAM-RD | DoD Enterprise Identity, Credential, and Access Management (ICAM) Reference Design, Version 1.0, June 2020 | https://dodcio.defense.gov/Portals/0/Documents/Cyber/DoD_Enterprise_ICAM_Reference_Design.pdf | Opened in browser; 123-page PDF, cover states Version 1.0, June 2020, prepared by DoD CIO.
DoDI-8520.03 | DoDI 8520.03, Identity Authentication for Information Systems, May 19, 2023 | https://www.esd.whs.mil/Portals/54/Documents/DD/issuances/dodi/852003p.pdf | Downloaded and text-extracted; sections 3.2, 3.3, 3.4, 3.6 cited.
NIST-800-53r5 | NIST SP 800-53 Rev. 5 (including Update 1), Security and Privacy Controls for Information Systems and Organizations | https://csrc.nist.gov/pubs/sp/800/53/r5/upd1/final | Opened; CSRC publication page.
NIST-800-63-4 | NIST SP 800-63-4, Digital Identity Guidelines (supersedes SP 800-63-3, withdrawn August 1, 2025) | https://www.nist.gov/publications/nist-sp-800-63-4-digital-identity-guidelines | Opened; NIST publication page. SP 800-63-3 CSRC page states withdrawal and supersession.
NIST-800-207 | NIST SP 800-207, Zero Trust Architecture, August 2020 | https://nvlpubs.nist.gov/nistpubs/SpecialPublications/NIST.SP.800-207.pdf | Downloaded and text-extracted.
ASD-STIG | DISA Application Security and Development STIG (V-2224xx / V-2226xx rule identifiers as published on STIG Viewer) | https://www.stigviewer.com/stig/application_security_and_development/ | Opened; rule identifiers and titles extracted from the page listing.
DAF-ZT | Department of the Air Force Zero Trust Strategy, Version 1.0, and DAF Enterprise Zero Trust Roadmap and Release Notes v2.0 (publication date 23 October 2024) |  | Located by web search on the DAF CIO public site; the site could not be resolved from the assessment environment, so the documents were not opened. Cited by title only. Government to furnish.
DAF-ICAM | DAF ICAM implementation direction (not publicly available) |  | No authoritative public document located. Rows referencing this source are marked 'Needs Government input'.